## Feature Tracker
Done | Priority | Feature Area | Current Status | Evidence / Gap | Owner | Notes
FALSE | Done | Four roles: Admin, Sub Admin, Manager, Sales Representative | Implemented | `UserRole` exists in `src/lib/types.ts`; UI exposes all roles in admin user forms.
FALSE | Done | Admin/Sub Admin same access level | Implemented | Admin page access and workflow checks use `admin` or `sub_admin`.
TRUE | P0 | All roles can view all units | Implemented | Client permissions now allow every role to view every unit; Supabase migration 0012 updates the units select policy and list_units_safe RPC while preserving owner-data masking.
FALSE | P0 | Owner phone visible only to Admin/Sub Admin/uploading Sales Rep | Not implemented | Managers can view owner data for team units in client and safe RPC logic.
FALSE | P0 | Owner phone search only for Admin/Sub Admin | Not implemented | `canSearchOwnerPhone` delegates to owner-data visibility, so managers and uploading sales users can search in cases the PRD forbids.
FALSE | P1 | Uploader name visible globally on cards/details | Not implemented | `createdByName` exists, but unit cards show project/type/owner phone; details do not include an uploader row.
FALSE | Done | No self-service password editing | Implemented | Profile page is read-only and has no password editor.
FALSE | Done | Admin/Sub Admin reset/edit user passwords | Implemented | Admin UI has set-password form and Supabase edge function `admin-update-user-password`.
FALSE | Done | Admin/Sub Admin user creation/edit/deactivation | Implemented | Admin UI and edge functions support user creation/profile updates; local workflows deactivate users.
FALSE | P1 | Sales representative deletion/deactivation requires reassignment | Not implemented | Reassignment exists, but prior assignment history is only in audit metadata; no durable per-unit ownership-history model. UI still labels the action as delete, not deactivate.
FALSE | Done | Inactive users remain visible in audit history | Implemented | Users are marked inactive/deletedAt locally and audit rows store actor name/role.
FALSE | P0 | Branches do not restrict unit visibility | Implemented | Client unit permissions, safe unit RPCs, manager analytics, and analytics RPCs no longer scope visibility by team or branch; team/branch remain metadata for filtering and reporting.
FALSE | Done | Users cannot self-register | Implemented | App exposes sign-in only; README instructs disabling public signup; seed/admin functions support admin-created accounts.
FALSE | Done | Multiple active sessions allowed | Implemented | No app-level single-session enforcement was found; Supabase default multi-session behavior is used.
FALSE | Done | Main pages: login/dashboard/units/create/details/notifications/profile | Implemented | `View` union and app navigation include these screens.
FALSE | Done | Extra admin pages: admin dashboard/user management/audit log | Implemented | Admin shell includes Users, Settings, Metrics, Audit.
FALSE | P1 | Extra admin pages: unit management/master data management | Not implemented | No UI to create/edit/archive Developer, Destination, Project, View, Finish, Teams, Branches, media limit, logo, or PDF layout.
FALSE | P1 | Sales dashboard PRD details | Not implemented | Dashboard exists, but latest units are visible units, not specifically logged-in sales user uploads; no sales 72-hour upload warning.
FALSE | Done | Manager dashboard PRD details | Implemented | Manager dashboard shows team uploads, team activity, status changes, installment updates, inactivity alerts, and quick actions.
FALSE | P1 | Admin/Sub Admin dashboard PRD details | Not implemented | Admin uses generic dashboard plus analytics/admin panels; PRD-specific dashboard sorting by teams/developers/destinations/projects is incomplete.
FALSE | Done | Any user can create a unit | Implemented | Create Unit is available to all non-admin-restricted views; RLS permits active users to insert units.
FALSE | P0 | Unit archive only Admin/Sub Admin | Not implemented | `canArchiveUnit` and RLS allow managers to archive team units.
FALSE | Done | Archive instead of permanent unit delete | Implemented | Units use `archived`; no normal UI hard-delete path found.
FALSE | P1 | Create Unit field order Destination before Developer | Not implemented | UI order is Developer, Project, BUA, Destination.
FALSE | P1 | Required field star/asterisk across forms | Not implemented | Required inputs exist, but labels do not consistently show `*`.
FALSE | P1 | Destination retained in creation/details/filters/PDF | Not implemented | Present in create/details/filters/PDF text, but order is wrong and PDF is otherwise incomplete.
FALSE | P1 | Destination not used in unit code | Not implemented | Client and DB generate unit code from destination label and include unit id/bathroom count.
FALSE | P1 | Fixed 12 unit types | Not implemented | Create UI offers only Apartment, Villa, Townhouse; seed lookup has Apartment/Villa only.
FALSE | P1 | Unit-type conditional fields | Not implemented | Floor, land area, furnished, finish, etc. are broadly shown; no 12-type conditional logic.
FALSE | P1 | Floor supports Ground and 1-40 only where applicable | Not implemented | Floor options include Ground, 1-40, and Roof; not tied to selected unit type.
FALSE | P1 | Penthouse wording and Penthouse unit behavior | Not implemented | Penthouse is absent from unit-type options and data model has no terrace-area field.
FALSE | P1 | Unit code formula Project Abbreviation + Bedrooms + BR | Not implemented | Current formula is destination-derived + id + BR + bedrooms + bathrooms.
FALSE | Done | One payment method per unit | Implemented | `PaymentMethod` is cash/installment and DB has `one_payment_method` constraint.
FALSE | Done | Basic total/down-payment/remaining/commission/installment math | Implemented | Domain and DB calculate remaining, commission, and installment amount for numeric installment years.
FALSE | P1 | Payment Method shown in details but excluded from PDF | Not implemented | PDF text/blob include payment method.
FALSE | P1 | Transfer fees | Not implemented | No type/schema/UI/PDF field found.
FALSE | P1 | Maintenance paid/cost/due-date fields | Not implemented | No type/schema/UI fields found.
FALSE | P1 | Custom installment text entered by user and shown in PDF | Not implemented | Custom mode exists, but no custom text input/storage/PDF field; PDF uses generic message.
FALSE | P1 | Installment From/To month-year selectors | Not implemented | UI/schema use numeric `installmentYears`.
FALSE | P1 | Payment timetable that marks installments paid/unpaid | Not implemented | Schedule is display-only; no payment history, mark-paid action, or remaining-value recalculation from timetable.
FALSE | P1 | Remaining Value locked except timetable changes | Not implemented | No edit workflow exists, and DB trigger recalculates remaining on any unit update from total/down payment.
FALSE | Done | Installment amount range filtering | Implemented | Client and Supabase safe search include installment amount range filters.
FALSE | Done | Owner country code/global phone normalization | Implemented | Client supports multiple country codes and normalizes; DB has `normalize_owner_phone`.
FALSE | Done | Duplicate block only same project normalized phone | Implemented | Client workflow and DB unique index enforce project + normalized phone; cross-project is allowed.
FALSE | Done | Delivery Date year-only and future years | Implemented | Create form stores delivery year only and supports 2026-2035.
FALSE | Done | Media limit 10 files / 40 MB total with clear errors | Implemented | Client validation enforces file count/total bytes and shows errors.
FALSE | P1 | Videos rejected everywhere | Not implemented | UI file input accepts images only, but types/schema/seed still support video, gallery has video placeholder, analytics counts videos.
FALSE | P1 | Permitted PDF attachments with at least one photo | Not implemented | Upload UI accepts images only; no PDF attachment support or related-photo rule.
FALSE | P1 | Image Show in PDF / Hide from PDF controls | Not implemented | No per-image include/exclude state or UI found.
FALSE | P1 | Download uploaded photos | Not implemented | Gallery displays media but no download action found.
FALSE | P1 | Remove uploaded images one-by-one while editing | Not implemented | Removal exists only before create submission; no edit-unit media workflow.
FALSE | P1 | Sales notes | Not implemented | Sales notes are created and shown, but no post-create edit workflow exists.
FALSE | Done | Admin/manager notes with metadata | Implemented | Admin/Sub Admin/Manager can add/update/delete a shared note with creator, role, timestamp.
FALSE | Done | Sales notified when admin/manager comments on own unit | Implemented | Note workflow creates in-app notification targeted to unit creator.
FALSE | P1 | Status: Available, Hold, Sold by Us, Sold by Others | Not implemented | Status enum has only `available`, `hold`, `sold`; UI has Mark Hold and Mark Sold.
FALSE | P1 | Status visible in cards/details/filters/audit/PDF | Not implemented | Status is visible in app/audit, but not split into Sold by Us/Others and not clearly included in PDF.
FALSE | Done | View All Units project/location-first cards | Implemented | Units page shows destination cards, then project cards, then units.
FALSE | P1 | Selected location/project opens separate page | Not implemented | Selection filters within the same `#units` view; no separate location/project route.
FALSE | P1 | Searchable/typeahead dropdowns throughout | Not implemented | Custom select components are button/listbox controls, not text-searchable inputs.
FALSE | P1 | Filters listed in PRD | Not implemented | Many filters exist, but land area, terrace area, garden area, split sold statuses, and strict owner-phone permissions are missing.
FALSE | Done | Unit Details route `/#details/:unitId` | Implemented | Hash detail route exists.
FALSE | P1 | Unit Details edit action for allowed users | Not implemented | No visible edit-unit action or edit page/workflow found.
FALSE | P1 | Unit Details compact mobile-first redesign | Not implemented | Details page exists, but section order and several required conditional-display rules do not match PRD.
FALSE | P1 | Unit Details Destination before Developer | Not implemented | Main info shows Developer, Project, then Destination.
FALSE | P1 | Unit Details Delivery before Commission | Not implemented | Commission is inside Pricing before Delivery.
FALSE | P1 | Unit Details Furnished only when selected | Not implemented | Details always shows furnished/unfurnished.
FALSE | P1 | Unit Details conditional fields only when applicable | Not implemented | Floor, land area, roof/garden area, furnished, etc. are shown even when not applicable.
FALSE | Done | Internal unit share link respects permissions | Implemented | Share link copies hash details route; detail selection uses visible/sanitized unit data.
FALSE | Done | PDF generation/share/download fallback | Implemented | Client generates PDF, uses Web Share where available, and downloads when sharing is unavailable.
FALSE | P1 | PDF branded with Leadra logo | Not implemented | PDF uses company name; no logo embedding/config UI found.
FALSE | P1 | PDF required content and ordering | Not implemented | Missing developer, down payment, remaining value, transfer fees, custom text, conditional area rules; includes payment method despite PRD exclusion.
FALSE | P1 | PDF selected-image inclusion/exclusion | Not implemented | PDF includes all image media; no Show/Hide PDF controls.
FALSE | Done | PDF audit/admin notification | Implemented | App records audit and admin notification when generating/sharing PDF.
FALSE | P1 | Admin-configurable PDF logo/name/footer/contact/layout | Not implemented | Settings model includes name/footer/contact/logo path, but UI only edits commission percentage.
FALSE | Done | Audit log baseline | Implemented | Audit rows are created for user, unit creation, archive/status, notes, PDF, settings/password flows.
FALSE | P1 | Full audit event coverage from PRD | Not implemented | Missing login/session revocation, edit-unit/payment timetable, image show/hide/download/remove, master-data changes, and several payment/maintenance events.
FALSE | Done | In-app notifications | Implemented | Notification center and workflow-created in-app notifications exist.
FALSE | P1 | Email notifications | Not implemented | Edge function exists, but no invocation/integration from app workflows found.
FALSE | P1 | 72-hour inactivity notifications | Not implemented | Manager/Admin dashboards display stale users; no notification-sending workflow found.
FALSE | Done | Profile account display | Implemented | Profile shows name, email, phone, role, team, branch, status.
FALSE | Done | Profile self-edit restrictions | Implemented | Profile page does not allow direct edits to password/role/team/branch/email.
FALSE | P1 | Profile phone edit if allowed by Admin/Sub Admin | Not implemented | No profile edit workflow found.
FALSE | Done | Mobile-first UI priority | Implemented | CSS/app structure is mobile-first oriented with touch-friendly cards/buttons, though detailed visual QA was not part of this pass.

## Summary
Metric | Value
Total tracked features | 83
Implemented | 32
Not implemented | 51
Completion % | 38.55%